## Sheet1
Project Name | Address Book
Start Date | 2024-06-05
End Date | 2024-10-05
Estimate | 2024-10-05
| Login | Register Page | Home Page | create and edit contact | delete | contact details | Total
UI | 2hr | 2hr | 4hr | 4hr | - | 2hr | 14hr
Validation | 1hr | 1hr | - | 2hr | 15min | - | 4:15hr
Back end | 1hr | 1hr | 11hr | 3:45hr | 30min | 2hr | 19:15hr
data base | 30min | - | 1:15min | 15min | 15min | 15min | 2:30hr
| 4:30hr | 4hr | 16:15hr | 10hr | 1hr | 4:15hr | Total 40hrs